## Sheet2
Task Name | Start DATE | Duration | END DATE
Search for Topic | 2014-10-05 | 1900-01-12 | 2014-10-18
Search resources | 2014-10-12 | 1900-01-12 | 2014-10-25
Algorithm of Design | 2014-10-12 | 1900-01-19 | 2014-11-01
Project Proposal | 2014-10-19 | 1900-01-19 | 2014-11-08
Schedule plan | 2014-10-19 | 1900-01-19 | 2014-11-08
Write the code frame | 2014-11-02 | 1900-01-12 | 2014-11-15
Write the code | 2014-11-09 | 1900-01-19 | 2014-11-29
Simulation | 2014-11-09 | 1900-01-19 | 2014-11-29
Final Report | 2014-11-16 | 1900-01-12 | 2014-11-29
Presentation | 2014-11-23 | 1900-01-05 | 2014-11-29
Formulas:
Duration = [END DATE]-[Start DATE]

## Sheet1
Task Name | October |  |  |  | November
| Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4
Search for Topic | bar: October Week 2 to October Week 3
Search resources | bar: October Week 3 to October Week 4
Algorithm of Design | bar: October Week 3 to October Week 5
Project Proposal | bar: October Week 4 to November Week 1
Schedule plan | bar: October Week 4 to November Week 1
Write the code frame | bar: November Week 1 to November Week 2
Write the code | bar: November Week 2 to November Week 4
Simulation | bar: November Week 2 to November Week 4
Final Report | bar: November Week 3 to November Week 4
Presentation | bar: November Week 4